## Sheet1
Timeline by Noonan Linehan Carroll Coffey LLP Solicitors. 17 November 2025
| Indaver | Planning authorities | EPA | High/Supreme Court | EU
2000
2000 | *Acquire site from Ispat
2001 | *lodge planng app for
haz incinerator only
2002 |  | Cork Co Mgr supports app
2003 |  | *S.4 Motion fails
| *appeal to ABP | *Permission refused
*ABP oral hearing 13 days
2004 |  | *Inspector recommends refusal
|  | *Permission granted |  | *12 people seek HCt JR | * NLCC complaint for CHASE
| *lodge waste lic app for |  |  |  | to Comm re failure to
| haz & muni incin @ EPA |  | *Proposed determination: licence |  | implement EIA Directive
|  |  | *Chase lodge appeal |  | (split juris etc)
2005 |  |  | *EPA oral hearing 2 weeks | *Apr SCt hears Martin case
*Inspector recommends grant
|  |  | *Licence granted | * Ringaskiddy Res Assoc
preps JR to HCt v EPA
2006 |  |  |  | * Both JRs deferred by HCt
pending SCt jmt in Martin
2007 |  |  |  | * May SCt Jmt, Martin loses
|  |  |  | * trial set for both JRs: Oct | *Comm announce intent to
bring Ireland to ECJ
|  |  |  | *Appls apply for adjnmt | re EIA Directive
|  |  |  | of both JRs, Reserved jmt | C-50/09
*HCt refuses adjmnt
*Refusal appealed to SCt
2008 | *Feb. Pre planning
| consult + ABP (SID) begins |  |  | *July, Sct rejects appeal
| *Nov. SID Plnng app for | *Sept. APB decision SID applies
haz & municipal incin
|  | ABP allows 8 wks for observations |  | *Dec, JRs withdrawn as
permission is expiring
2009 |  | *ABP Oral Hearing April-June
2010 |  | *Jan, ABP issue Further Info letter |  |  | *ECJ hearing of action
*April, Extension granted to Indvr
| *Aug, Indvr file reply | *Aug, Indvr file reply + ABP
*Observation period 6 weeks
2011 |  | *June 2011 Permission refused |  |  | *ECJ jmt against Ire, C-50/09
(*Inspector recommended refusal)
|  | * Limited costs order agst Indvr |  | * July, Indvr seek JR @ HCt
2012 |  |  |  | *May, Trial fixed for Oct
| *Aug, pre planing |  |  | *Oct, Indvr withdraws JR
| consult + ABP (SID) |  |  | *Dec, Costs hearing in HCt
waste to energy plant +
waste transfer station
2013 | continues |  |  | *Jan, Ltd Costs against Indvr
*Feb, Indaver withdraw
appeal request
2014 | continues
2015 | Indaver NV sold to Katoen Natie
23 Dec. ABP says it is SID
2016 | ABP: 9 March deadline for public | 20 Jan Application published
ABP Oral Hearing April-May (17 days)
2018 |  | ABP Grant Permission 29 May |  | *July CHASE seeks HCt JR
2019 |  |  | *June Indaver submit application to EPA | *Jan Discovery hearing
|  |  | for IE licence | *Feb Discovery judgment
|  |  | *Aug EPA validate Indaver application | *March Hearing (9 days)
*Sept EPA request extension for decision
2020 |  |  | *Jan EPA request extension for decision
*May EPA request extension for decision
*Sept EPA request extension for decision
*Nov EPA request further information
2021 |  |  | *Jan Indaver reply to request for further info | *19 March High Court Judgment
|  |  | *March EPA request extension for decision | *8 Jun Remittal Hearing
|  |  | *July EPA request info from Indaver on case | *1 October Remittal Judgment
|  |  | following remittal hearing and will not | *26 Nov Cert of Appeal Hearing
commence 8 weeks for PD until received
2022 |  |  | *March Indaver has not responded to the EPA's request to date | *September Supreme Court Determination
2023
2024 |  | *Jan ABP reactivate remitted application
PA04.318802
*July ABP invite Indaver to file FI deadline
2025-06-30
2025 |  | *May ABP Receive and grant Indaver
request to extend time for FI response
| *Aug ABP receive RFI | *Sept ACP Notify public and CHASE of FI
receipt and of it being deemed
Significant
*Oct Indvaer set 17 Nov as deadline for
observations to ACP