## Sheet1
Item No | Item Name | Produced by | Status | Format | CD | % Complete
1 | Cover Letter | WMG | Complete | PDF |  | 95
2 | Issue Sheet Register | WMG | Letters bodies | Excel |  | 95
3 | AA Planning Application Checklist | WMG | Complete | Excel |  | 95
4 | Newspaper Notice | WMG | Dates to be confirmed | PDF |  | 92.5
5 | Site Notice | WMG | Signature Required / Dates to be confirmed | Word |  | 92.5
6 | List of Prescribed Bodies | TCC - Paul Crowe | TCC to confrim current list of bodies | Word |  | 92.5
7 | letter to prescribed bodies | TCC - Paul Crowe | To be finsilased once TCC happy with List | Word |  | 85
8 | Architectual & Engineer Design Report | WMG | Complete | PDF |  | 95
9 | Construction & Environmental Mgt Plan | WMG | Complete | PDF |  | 95
10 | Architectual Heritage Imapct Assessment | kate | Complete | PDF |  | 95
11 | Appropriate Assessment Screening Report | Flynn Furney | Complete | PDF |  | 95
12 | Natura Impact Statement | Flynn Furney | Complete | PDF |  | 85
13 | Ecological Impact Assessment (EcIA) | Flynn Furney | Complete | PDF |  | 95
14 | Invasive Species Managemnt Report | Flynn Furney | Complete | PDF |  | 95
15 | Drawings etc | WMG | Complete | PDF |  | 95
16 | Flooding Risk asssesment | WMG (ZG) | To be checked due to be issued 23/10/25 | Word |  | 80
print full suite fo letters list 14 no plus the CD. 15 CD's for them.
3 Sets
CD's to be left at clonmel office and shipped up.

## Issue Sheet
[5 empty] | Job | Newport Foot Bridge Bridge
[5 empty] | Client | Tipperary County Council
[5 empty] | Status | Planning
Document Register
Document Number | [6 empty] | Document Name | Status | Format
Job Number | Originator | Zone | Level | Type Code | Discipline | Sheet Number | Sheet Name
7766 | WMA | XX | XX | LT | A | 0 | Cover Letter | Planning | pdf
7766 | WMA | XX | XX | RP | A | 1 | Document Register | Planning | pdf
7766 | WMA | XX | XX | RP | A | 2 | AA Planning Application Checklist | Planning | pdf
[7 empty] | Newspaper Notice | Planning | pdf
[7 empty] | Site Notice | Planning | pdf
[7 empty] | List of Prescribed Bodies | Planning | pdf
7766 | WMA | XX | XX | RP | A | 1 | Project Explanary Design Report | Planning | pdf
7766 | WMA | XX | XX | RP | A | 2 | Construction Environmental Management Plan | Planning | pdf
| FFE | XX | XX | RP | E | 3 | Newport Ball Ally Footbridge EIA Screening | Planning | pdf
| FFE | XX | XX | RP | E | 4 | Newport Ball Ally Footbridge AA Screening | Planning | pdf
| FFE | XX | XX | RP | E | 5 | Newport Ball Ally Footbridge Bat Survey Report | Planning | pdf
| FFE | XX | XX | RP | E | 6 | Newport Ball Ally Footbridge Invasive Species Management Plan | Planning | pdf
| FFE | XX | XX | RP | E | 6 | NIS Newport Ball Ally Footbridge
J25-43 | [6 empty] | Newport-Ball-Alley-Footbridge_Desktop-Report | Planning | pdf
[7 empty] | Letters to Prescribed Bodies | Planning | pdf
[7 empty] | Site Context Map 1_10560 | Planning
[7 empty] | Site Location Map | Planning | pdf
7766 | WMA | ZZ | ZZ | DR | A | 1000 | Proposed Site Plan | Planning | pdf
7766 | WMA | ZZ | ZZ | DR | A | 1001 | Proposed Plan | Planning | pdf
7766 | WMA | ZZ | ZZ | DR | A | 1002 | Bridge Plan and Sections | Planning | pdf
OPW Section 50 Application Form
OPW Section_50_Newport Ball Ally Footbridge Co. Tipperary Response
Letters of Ownership / Consent
Distribution
Recieving Entitiy | [6 empty] | Status | Copies | Date
Tipperary County Council | [6 empty] | Planning | 1 | TBC
An Bord Pleanala | [6 empty] | Planning | 1 | TBC